Global Data Facility — Mobile Phone Data for Policy (GDF-MPD)

Program Status Briefing Note

DRAFT — 14 September 2026  |  For internal discussion  |  Prepared by the GDF-MPD core team

# 1.  Overview

The program is the largest global initiative of its kind, currently supporting 24 country programs across Cohort 1 (global window) and Cohort 2 (SADC window), with a goal of reaching 30 countries by 2030. Core support delivery is well advanced: foundational knowledge assets, governance templates, training curriculum, and the knowledge portal have all been delivered, and the program maintains a steady presence at leading global data and statistical convenings. The implementation period for the 18 country initiatives in Cohort 1 concludes in late 2026, with final results to be collected and disseminated in 2027. The Cohort 2 implementation period, which involves 6 grant receiving countries (16 received training), concludes in the first half of 2027, with country-level results to be disseminated by end of 2027.

This note summarizes progress and status to date across the program's two pillars. Pillar 1, Country Operational Support, comprises the Core Support Program (Component 1) and the Country Cohort initiatives (Component 2). Pillar 2 is the Research Program.

| Item | Detail |
| --- | --- |
| Program | Global Data Facility — Mobile Phone Data for Policy (GDF-MPD) window |
| Funding Partner | Government of Spain, Ministry of Economy, Commerce and Business |
| Managing Partnership | Development Economics VP; Fiscal Policy and Growth (FPG) Digital Development VP; International Telecommunications Union |
| Technical partner | International Telecommunication Union (ITU) |
| Country Coverage | 25 country initiatives with operational pillar grants (Cohort 1: 19; Cohort 2 / SADC: 6); 16 countries received observer and or in-kind support; |
| Knowledge portal | worldbank.github.io/GDF-MPD |
| Youtube Channel | https://www.youtube.com/@GlobalDataFacility/videos |

Table 1. Program at a glance.

# 2.  Pillar 1 — Country Operational Support

Pillar 1 delivers the program’s operational support program to World Bank country teams. It has two components: the Core Support Program, which supplies the essential resources, public goods, convening and advisory capacity of the window; and the Country Cohort initiatives, which apply that offer through funded country-level engagements.

## 2.1  Component 1 — Core Support Program

The Core Support Program delivers the knowledge and learning assets, the methodological and governance assets, the training curriculum, the knowledge portal, global partnerships, convening and communications, and the direct operational advisory support. Nearly all the knowledge and learning foundational assets planned through FY26 have been delivered; the remaining pipeline is concentrated on the standard processing pipeline, pipeline costing estimates, and applied methodologies with base code.

### 2.1.1  Knowledge and learning— Flagship Resources

### The GDF-MPD Program has made programmatic investments in building the technical and institutional capacity needed to sustain national MPD pipelines. Through a mix of in-person workshops, instructor-led online courses, and open-access public goods, the program has delivered structured learning opportunities to country teams across both cohorts. The table below summarizes flagship training activities and major workshops delivered or planned under the program.

| Date | Flagship Activity/Resource | Format |
| --- | --- | --- |
| 7–10 Oct 2024 | Cohort 1 Launch Workshop — Washington, DC (held alongside NetMob 2024) | 5-day in-person launch workshop |
| 19–22 May 2025 | Cohort 2 (SADC) Launch Workshop — Johannesburg, South Africa | 5-day in-person launch workshop; held ahead of the call for proposals so country teams could use their proposals as workplans |
| 2025 | GDF YouTube channel – over 2 dozen MPD videos | Open access |
| Sep 2025 | Mobile Phone Data Knowledge Portal | Open access |
| Sep–Oct 2025 | Cohort 1 — MPD Foundations in Policy, Practitioner Track (Open Learning Campus) | 5 weeks, instructor-paced, online |
| Oct–Dec 2025 | Cohort 1 — MPD Foundations in Policy, Technical Track (Open Learning Campus) | 8 weeks, instructor-paced, online |
| Apr 2026 | Data Academy — MPD Foundations in Policy, Practitioner Track | Open Access, Self-paced, Online |
| Apr 2026 | Data Academy — MPD Foundations in Policy, Technical Track | Open Access, Self-paced, Online |
| Oct 2026 (planned) | SADC Regional Technical Workshop (6 countries) | 5 day, F2F training |

### Table 2. Flagship training programs, cohort launch workshops and course rounds.

### 2.1.2  Knowledge and learning— foundational resources

| Key deliverable | Planned | Status |
| --- | --- | --- |
| Integrated MPD Ecosystem — Theory of Change | Jun/25 | Delivered |
| Country Maturity Assessment Framework and Tool | Jun/25 | Delivered |
| MPD Foundations Training — curriculum and content | Jun/25 | Delivered |
| Cohort launch video | Oct/24 | Delivered |
| MPD Foundations Course — Practitioner Track (Open Learning Campus) | Jun–Sep/25 | Delivered |
| MPD Foundations Course — Technical Track (Open Learning Campus) | Sep–Dec/25 | Delivered |
| GDF-MPD Knowledge Portal | Jan/26 | Delivered |
| Mobile Network Operator — Readiness Questionnaire | Jan/26 | Delivered |
| MOU templates (English / French) | Oct/25 | Delivered |
| WB Enhanced MPD Data Sharing Agreement | Feb/26 | Delivered |
| MPD Pipeline — access and governance templates | Jan/26 | Delivered |
| Tourism methodology | TBC | In progress |
| Migration methodology | TBC | In progress |
| Standard MPD processing pipeline software | Jan/27 | Planned |
| MPD pipeline — costing estimates survey and guidelines | Dec/26 | Planned |
| MPD management and workflow processing open-source software | Jun/27 | Planned |
| Country press release toolkit | TBC | Planned |
| AI-assisted workflow for country maturity assessment | TBC | Planned |
| MPD governance framework and tools | Dec/26 | Planned |

Table 3. Core knowledge, governance and methodological assets.

### 2.1.3  Conferences, events and workshops

### The GDF-MPD Program has maintained an active presence at leading international data and statistics fora, advancing the global agenda on responsible mobile phone data use. This engagement has been strengthened through a valued partnership with the International Telecommunication Union (ITU) and the UN Task Team on Mobile Phone Data (under the Committee of Experts on Big Data and Data Science, UN-CEBD), which has provided a platform for the program to contribute to and shape evolving global standards, methodologies, and policy frameworks. Together, these collaborations have ensured that country-level implementation experience feeds into global discourse, and that international best practices inform program delivery. The table below captures key conference participations, side events, and engagements at international fora over the program period.

| Date | Conference / event / workshop |  | Session |  |
| --- | --- | --- | --- | --- |
| 23–24 Sep 2024 | WTIS-24 — 19th World Telecommunication/ICT Indicators Symposium (Geneva) |  | Mobile phone big data: from methods to implementation |  |
| 10–14 Jun 2024 | 8th International Conference on Big Data and Data Science for Official Statistics |  | Putting MPD to Work: Theory, Tools, Tactics |  |
| 7–10 Oct 2024 | GDF-MPD Cohort 1 Launch Workshop & NetMob 2024 (Washington, DC) |  | Cohort 1 Launch Workshop |  |
| 12–15 Nov 2024 | 5th UN World Data Forum (Medellín, Colombia) |  | Crossing the Chasm: Putting MPD to Work for Policy |  |
| 4 Mar 2025 | 56th Session of the UN Statistical Commission — side event (New York) |  | Unlocking the Potential of Mobile Phone Data for Official Statistics |  |
| 9–10 Apr 2025 | MNO-MINDS ESTP Training Course — Eurostat / Istat / Statistics Austria (Vienna) |  | MNO data: methods for integrating new data sources in official statistics |  |
| 19–22 May 2025 | SADC Regional Workshop (Johannesburg) — Cohort 2 launch |  | SADC Mobile Phone Data for Policy Regional Workshop 2025 |  |
| Jun 2025 | LAC — UN Big Data Regional Hub |  | MPD for Policy webinar |  |
| Jun 2025 | Poverty Summer Academy |  | MPD session |  |
| 17 Jun 2025 | UN 2.0 Innovation Network webinar (online) |  | Global Push to Put Mobile Phone Data to Work for Policy |  |
| 30 Jun – 3 Jul 2025 | 4th International Conference on Financing for Development (Sevilla) — side event |  | Putting Mobile Phone Data to Work for Policy |  |
| 22–23 Sep 2025 | WTIS-25 — 20th World Telecommunication/ICT Indicators Symposium (Geneva) |  | Scaling use of Mobile Phone Data for Official Statistics |  |
| 23–25 Sep 2025 | MNO-MINDS Final Conference — Eurostat / OECD (Paris) |  | Integrating MNO data with other sources to produce official statistics |  |
| 23 Sep 2025 | IPC Business Summit (Lima, Peru) |  | From AI Advances to Business Impact |  |
| 2–5 Oct 2025 | Digital Bridge (Astana, Kazakhstan) |  | Program participation |  |
| 8–10 Oct 2025 | NetMob 2025 — CNAM / Inria (Paris) |  | World Bank presentations on mobile phone data for development |  |
| 17 Oct 2025 | World Bank–IMF Annual Meetings 2025 (Washington, DC) |  | Mobile Phone Data Policy Applications in Jobs |  |
| 8 Dec 2025 | UN Regional Hub webinar (online) |  | ITU Jupyter Notebooks: a practical tool for analysing mobile phone data |  |
| 9 Dec 2025 | ILO "Global Challenges — Global Solutions" podcast (online) |  | Big Data: what it is, what it does, and how it impacts the world of work |  |
| 10 Dec 2025 | UNFPA–UNECE webinar (online) |  | Use of Mobile Phone Data in Official Statistics |  |
| 2 Mar 2026 | Mobile World Congress |  | Session cancelled |  |
| 9–11 Mar 2026 | 57th Session of the UN Statistical Commission — side event (New York) |  | Dialing up Mobile Phone Data for Statistics |  |
| 2–13 Mar 2026 | ECOWAS Mobile Phone Data for Statistics Workshop (Abidjan) — HISWACA / GDF-MPD |  | Launch of the ECOWAS Technical Working Group on MPD for Policy |  |
| 12–14 May 2026 | 20th IAOS Conference (Vilnius, Lithuania) |  | Sessions on mobile phone data for official statistics |  |
| 16–23 May 2026 | São Tomé and Príncipe national workshop |  | Country workshop |  |
| 2–5 Jun 2026 | Global Data Festival 2026 & Kenya Space Expo (Nairobi) |  | Dialing up Mobile Phone Data for Policy |  |
| 7–10 Jun 2026 | 10th Mobile Tartu Conference & PhD School (Tartu, Estonia) |  | World Bank session: challenges in MPD research |  |
| 9–11 Jun 2026 | Digital Enterprise Show (DES) 2026 (Málaga, Spain) |  | Mobile Phone Data for Policy showcase |  |
| 6 Jul 2026 | WSIS Forum 2026 (Geneva) — ITU / UNESCO / UNDP / UNCTAD |  | Dialing up Mobile Phone Data for ICT Statistics |  |
| 7–9 Sep 2026 | WTIS-26 — 21st World Telecommunication/ICT Indicators Symposium (Geneva) |  | GDF-MPD / UN-CEBD MPD Task Team participation |  |
| 8–10 Sep 2026 | 10th Data for Policy Conference (Barcelona) — Universitat Pompeu Fabra |  | Governance of / with AI: implications for data, infrastructure and tech sovereignty |  |
| Sep 2026 | UN Big Data Regional Hub for Latin America and the Caribbean (Brazil) — IBGE / ENCE |  | TBA |  |
| Date | Conference / event | Session |  | Status |
| 19 Oct 2026 | SADC Technical Workshop | Cohort 2 technical session |  | In preparation |
| 14-16 Oct | Netmob, (Brazil) |  |  |  |
| 9–12 Nov 2026 | 6th UN World Data Forum (Riyadh) — GASTAT / UNSD | Sessions on innovation, partnerships and trust in data |  | In preparation |
| 2026 ( |  |  |  |  |

Table 4. Delivered conferences, events and workshops. The two cohort launch workshops also appear in Table 3; Confirmed and planned events, FY27.

### 2.1.5  Blogs and Multimedia

| Date | Item |
| --- | --- |
| 13 Nov 2025 | Blog: Working together to launch the world’s largest cohort working on mobile phone data for policy |
| 13 Jun 2025 | Blog: Dialing up the use of mobile phone data for policy in South Africa |
| 3 Apr 2026 | Blog: Scaling up mobile phone data for statistics in West Africa |
| 1 Jun 2026 | Blog and paper: Mobile phone data for poverty targeting |
| 2026 | Consolidated program input to the 2026 GDF Annual Report |
| In pipeline | Country press release toolkit; multi-media donor thank-you card (target Oct 2026) |

Table 5. Publications and communications products.

### 2.1.6  Core Operational Advisory and Technical Support

### The GDF-MPD Program oversees both the competitive grant-making process through which country teams are selected and funded, and the delivery of programmatic support through its Country Cohort engagement model. Beyond the technical assistance provided directly to country teams, the program also leads a portfolio of strategic activities designed to advance the broader agenda of responsible and effective mobile phone data use for policy.

| Activity | Projected | Status |
| --- | --- | --- |
| Cohort 1 — 18 country initiatives launched (two-year implementation window) | Nov 24 – Nov 26 | In progress |
| Cohort 2 — SADC window launched (12-18 month implementation window) | Jan 26 – Jun 27 | In progress; |
| ECOWAS Technical Working Group on MPD for Policy established | Mar/26 | Delivered |
| Participation in the Eurostat Multi-MNO and MNO Minds working group and fora | Jan 24-Jan 26 | Delivered |
| Mid-term Cohort One Strategic Review – Recommendations for Program Effectiveness | Nov 25 | Delivered |
| SADC Technical Workshop, Botswana | Oct 26-30 |  |
| Pilot enhanced technical assistance approach in 3-4 countries | Jan 27 | Planned |
| Ad-hoc advisory support to operational teams | Ongoing | (see Section 2.2.3) |

Table 7. Program operational support, e.g. Data Scientists, Economists provide cross-support to the Cohort teams

## 2.2  Component 2 — Country Cohort Initiatives

The program supports over 24 country initiatives across two cohorts. Cohort 1 (18 countries, launched November 2024) is global; Cohort 2 (6 countries, launched May 2025) is the SADC window. Progress diverges, Ecuador, Kazakhstan, The Gambia, Mongolia and Brazil have reached practitioner level of maturity, while a substantial group remains at pre-foundation stage, where the binding constraints are typically legal and institutional. Tourism statistics is the most frequently scoped use case, followed by urban mobility and transport.

### 2.2.1  Cohort 1 — Global  (18 countries)

| Country Team / TTL | Project title / use case | MOU status | Maturity | Top-up (Y/N) | Notes |
| --- | --- | --- | --- | --- | --- |
| Argentina | Dynamic population mapping; information society statistics | No MOU documented | Pre-Foundation | N | - Telefonica sale put a pause on Regulator engagement with the project. - ITU Magpantay has established contact with a separate government team - Marianna is considering options |
| Benin | Dynamic population mapping; tourism statistics | No MOU documented | Pre-Foundation | N |  |
| Brazil | Transport and mobility statistics | MOU signed | Practitioner | N | -Stakeholder workshop in Brasilia (Feb 2025): 100+ representatives from ANATEL, Ministry of Cities, IBGE, SERPRO - Origin-destination matrices and mobility pilots launched for Florianópolis, Rio de Janeiro, and Belém - MPD analytics integrated into Brazil Electromobility MPA (electric bus transition) - DRM use case added following 2024 Rio Grande do Sul floods --LAC regional hub engagement (IBGE / ENCE) - Origin-destination matrices and mobility pilots completed for Florianópolis, Rio de Janeiro, and Belém - Analytical use case for Salvador urban transport, including providing concrete policy insights (completed in July 2026) - Final capacity building workshop planned for November 5, 2026, where the first half of the day will focus on the presentation of the policy insights emerging from the analytical case studies (Salvador urban transport, Rio Grande do Sul DRM, plus a presentation by IBGE on their efforts to develop a proof of concept with CDR for commuting statistics), and the second half of the day will be hands-on training on CDR use and caveats. I’m attaching the save-the-date if useful. |
| Côte d’Ivoire | Dynamic population mapping; migration statistics | MOU drafted, not signed | Pre-Foundation | N | - Hosted the ECOWAS MPD for Statistics Workshop, Abidjan, Mar 2026; founding member of the ECOWAS Technical Working Group. - MOU drafted with Orange. |
| Ecuador | Transport statistics; poverty mapping | MOU signed | Foundation | Y | - MOU signed - Pipeline provisioned; active data use under way. Strong Foundations Course uptake across INEC, MTOP, the Quito Secretariat of Mobility and OTECEL. - Use cases: national road network model, Quito Metro impact, canton-level poverty mapping. OTECEL dataset acquired with two weeks of QA technical support First interinstitutional MPD technical team created (INEC, MIT, OTECEL) - ML poverty estimation model developed (consultant from Universidad Carlos III de Madrid) - Informing Emergency Resilient Reconstruction Project (P181079) and Quito Metro Line One Phase II (P511841) |
| Guinea | Transport; urban mobility | No MOU documented | Pre-Foundation | N |  |
| Haiti | Dynamic poverty mapping for social assistance targeting | MOU drafted; existing DSA with Digicel (via Flowminder) under renewal | Foundation | N | - Counterparts include IHSI, MAST, DGPC and CNSA. - Flowminder-Digicel data sharing arrangement has been renewed – Flowminder are producing statistics with Digicel data - Digicel have also formally recognized Flowminder’s collaboration with the World Bank and IHSI. - Supporting IHSI to pursue a (direct) data sharing agreement with Natcom, Haiti’s second largest MNO (Sep 26) - Using Digicel’s MPD (processed by Flowminder) to help build/validate an integrated master sample for Haiti’s upcoming household surveys |
| India | Public health; crisis monitoring, Tourism | MOU signed | Foundation | Y | - It is among the first major studies in India to leverage high-volume mobility data to systematically map tourist movement patterns. - The scale and volume of data used are unprecedented for a tourism analytics exercise in the country. - Letter of Intent signed between Government of Maharashtra and Reliance Jio (Jul 2025) - Pilot completed mapping tourist patterns across Maharashtra with Jio, MITRA, Department of Toursim. - Preliminary results presented to Ministry of Tourism and MoSPI; featured at National Workshop on Alternate Data Sources (Jun 2025) - Preliminary tourism results circulated and reviewed through Bank processes (Jul 2026) - Top-up (Phase 2): scaling in Maharashtra through Bank lending operation and a second state (Goa or Odisha) |
| Kazakhstan | Tourism statistics (domestic and inbound) | MOU signed (Nov 2024); parliamentary decree mandating MPD sharing from Jan 2026 | Practitioner | Y | - MOU signed (Nov 24) - Advanced implementation with top-up funding. - Legislative mandate extends data sharing to all MNOs from Jan 2026. - Tourism statistic phase one official statistics launched at Digital Bridge, Astana, 30K attendees (Oct 2025) - Preliminary tourism statistics showed 2.4x–4x underreporting vs. official records (Jun 2025) - Advanced to Practitioner stage; multi-MNO integration and inbound tourism statistics underway - BNS ICC team took over all script development in-house, ensuring pipeline sustainability - Ministry of Tourism and Sport formally integrating MPD findings into infrastructure and strategic planning - First country in the CIS to transition MPD-derived indicators into official statistics - ICC produced a first set of commuting and migration statistics (June 2026) |
| Kenya | Dynamic population mapping; disaster response; transport | MOU signed Jul 26 | Foundation | Y | - MOU signed with Safaricom; KNBS, CA and ODPC engaged. Global Data Festival and Kenya Space Expo, Nairobi (Jun 2026) |
| Mongolia | Migration and information society statistics | MOU signed (2025) | Foundation | Y (proposal submitted) | -GDF workshop (Oct 2024): stakeholders aligned on migration use case for nomadic/rural-to-urban mobility gaps - -Tripartite MoU signed: Mobicom, CRC, and NSO (Jul 2025) - Follow-up workshop (Apr 2025) with Positium and ITU on data privacy and best practices - Phase 3 proposal submitted (Sep 26) - First use case completed: population and internal migration statistics; pipeline validated at National Data Center - Reached "Practitioner" maturity stage - Top-up: domestic tourism indicator framework under development; Phase 3 proposal submitted (Sep 2026) |
| Morocco | Dynamic vulnerability mapping; social assistance; migration | Pre-MOU | Practitioner | N | - Near-practitioner maturity despite pre-MOU status. - National workshop delivered in May 2026, convening NSO, Regulator and MNOs - Ongoing review of regulatory framework and preparatory negotiations for MOU |
| Peru | Disaster response; public health | DSA signed with INEI | Foundation | N | - Hosted GDF-MPD program at IPC Business Summit session, Lima, (Sep 2025) - DSA signed between INEI and the World Bank (May 26) |
| Rwanda | Vulnerability mapping; social assistance | MOU Pending | Foundation | N | - High-Level Roundtable (April 2025)Government (Ministry of Local Government, NISR, RISA, RURA), MNOs (MTN, Airtel), and development partners secured buy-in for MPD integration into Imibereho Social Registry. - MINALOC formally requested sample MPD dataset (5,000–20,000 subscribers) from RURA for operational research. - Multi-agency Technical Working Group formed (MINALOC, RISA, NISR, RURA). - Further exploration of MPD included in the Additional Financing for Social Protection Transformation Project (P177492). - Roundtable hosted by MINALOC, NISR, and RURA (July 2026) – Signed minutes attached - Revised DSA agreed by all parties; signature pending (August 2026) – Follow on meeting to unlock any pending issue planned during the week of September 12. |
| Senegal | Urban mobility and transport | MOU drafted | Foundation | N | - Research on temporary migration patterns under way. Member of the ECOWAS Technical Working Group (launched Abidjan, Mar 2026). - MOU drafted with Orange; ARTP engaged. |
| The Gambia | Dynamic population mapping; migration; urban mobility | MOU signed; Data License Agreement signed (2-year auto-renewable) | Foundation | N | - Tranche 1: study tour to Ghana; ECOWAS workshop; use case and IT pipeline developed; MPD Academy in The Gambia (June 2025); - MOU signed between PURA and GBoS; online GDF-MPD training completed. - Scale-up under the Stats Project, extension of the use case, and local literacy and capacity building. - GBoS is core member of the ECOWAS Technical Working Group (launched Abidjan, Mar 2026). - PET technology provisioned and training provided (May 2026). - WB DSA signed between PURA and WBG; PURA acts as data custodian and licensor (August 2026). |
| Togo | Migration and tourism statistics | No MOU documented | Pre-Foundation | N |  |
| Tunisia | Vulnerability mapping; social assistance; internal migration indicators | MOU drafted; letter to MNOs issued (Jun 2024) | Practitioner | N | - Letter to MNOs issued Jun 2024 - Country workshop convened (24) - technical meetings and a national workshop convened (Mar 25) |

Table 10. Cohort 1 country initiatives. MOU status from the MOU/DSA log; remaining columns for manual completion.

### 2.2.2  Cohort 2 — SADC window (6 countries)

| Country Team / TTL | Project title / use case | MOU status | Maturity | Top-up (Y/N) | Notes |
| --- | --- | --- | --- | --- | --- |
| Botswana | Tourism statistics | MOU signed; DSA near completion | Foundation | N | - National stakeholder workshop held Nov 2025, with BOCRA, Statistics Botswana, Mascom, Orange and BTC engaged. - MOU signed November 2025 - Steering Committee and Task Team established.(inauguration meetings held on Dec 2025 and April 2026) - Procurement of technical assistance to support the use of MPD for improved tourism statistics (focus on feasibility and capacity building) June-December 2026 - Institutional capacity and gap assessment report (July 2026) - DSA signed September 2026 |
| Madagascar | Poverty mapping | MOU pending legal review (data protection law compliance assessment) | Pre-Foundation; Early–mid | N | - National workshop held Mar 2026; an NSO-hosted model has been proposed. - MNO engagement paused pending legal clarity. |
| Malawi | ICT indicators; tourism statistics | MOU drafted | Pre-Foundation; Early–mid | N | - National workshop held Feb 2026, with Airtel and TNM engaged. - Technical Working Committee and NSO working group identified. - Next: finalize the MOU and establish a production environment on e-government infrastructure. |
| São Tomé and Príncipe | Tourism statistics | MOU drafted (INE–CST) | Pre-Foundation; Early–mid | N | - National workshop held May 2026; tourism confirmed as the priority use case. - Technical and governance focal points identified. - Next: validate the MOU between INE and CST and develop the tourism statistics pilot. |
| South Africa | Transport and mobility statistics | Existing MOU signed; formal data sharing not yet initiated (Jul 2026) | Foundation | N | - Stats SA project team designated; stakeholder outreach initiated and implementation planning under way. - Comprehensive business case document produced by Stats SA to support engagement - Next: legal review and formal data-sharing discussions with the regulator and MNOs. - Next: National stakeholder workshop planned for Oct 2026 |
| Zambia | Population mapping; tourism; internet access | MOU in preparation | Pre-Foundation; Early–mid | N | - Internal MPD team identified at ZamStats and an IT focal point designated. National workshop planned Aug–Sep 2026; - further mission is scheduled for Oct 2026 on either side of the SADC regional workshop - Next: establish a steering committee, undertake a legal review, and engage MNOs. Leadership changes at ZamStats have disrupted continuity. |
| Angola |  |  |  |  |  |
| Comoros |  |  |  |  |  |
| Democratic Republic of Congo (DRC) |  |  |  |  |  |
| Eswatini |  |  |  |  |  |
| Lesotho |  |  |  |  |  |
| Mauritius |  |  |  |  |  |
| Mozambique |  |  |  |  |  |
| Namibia |  |  |  |  |  |
| Seychelles |  |  |  |  |  |
| Tanzania |  |  |  |  |  |
| Zimbabwe |  |  |  |  |  |

Table 11. Cohort 2 country initiatives.

### 2.2.3  Cohort Observing Countries – participated in workshops, and received ad-hoc program support

Countries receiving considerable advisory support outside the two formal cohorts.

| Country | Type of support | Status | Entry point / counterpart | Notes |
| --- | --- | --- | --- | --- |
| Somalia | Small operational grant; Operational advisory support; Observer to SADC Technical Training | In progress | Alejandro De La Fuente, Senior Economist, POV | - MOU Signed - DSA drafted, pending validation - Received operational funding through East Africa Statistical Projected |
| Ukraine | Operational advisory support | In progress | Judy Yang, Senior Economist, POV | - Advice given on sampling frame and survey design to use listing data from MNO - Technical advisory support on standard migration and displacements statistics methodology |
| Nepal | Operational advisory support |  | Sariti Sapoka, Economist, SAR | - exploring scope for technical support in wake of flooding event (Sep 2026) |
| Maldives | Operational advisory support |  | Briton Laurin Rude, Economist, ESAPV | - UNDP workshop convened (2026) |
| Ghana | ECOWAS workshop training; operational advisory support |  |  |  |
| Nigeria | ECOWAS workshop training |  |  |  |

Table 12. Ad-hoc cross-support engagements.

### 2.2.4  Additional Countries that have requested program support

Expressions of interest received to date.

| Country | Region | Requested support / use case interest | Status of request | Next step | Notes |
| --- | --- | --- | --- | --- | --- |
| Azerbaijan | ECA | Request from regulator for technical support and operationalization of pipeline | Access to templates and training materials provided | Pending review for next cohort |  |
| Armenia | ECA |  |  |  |  |
| Dominican Republic | LAC |  |  |  |  |
| Cabo Verde | AFW |  |  |  |  |
| Colombia | LAC |  |  |  |  |
| Ghana | AFW | Public health; humanitarian and development planning; migration; SDG indicators | Under discussion (core team item #39) |  | Formal agreement with Vodafone Ghana and GSS signed in 2018 (3-year initial term). Member of the ECOWAS Technical Working Group launched Mar 2026. |
| Jamaica | LAC | Enable real-time monitoring of population displacement and mobility for hurricane response, as well as routine official statistics on topics such as tourism and migration. | STATIN requested support on the technical and institutional foundations needed to harness MPD from Jamaica’s two main MNOs STATIN have already signed a NDA with Flow and engaged with the Office of Utilities Regulation (OUR), to establish the requisite legal and technical working groups. Under discussion (core team item #40) |  |  |
| Kurdistan Region, Iraq | MENA |  |  |  |  |
| Liberia | AFW |  |  |  |  |
| Maldives | SAR |  |  |  |  |
| Malaysia | EAP |  |  |  |  |
| Mauritania | AFW |  |  |  |  |
| Mauritius | AFE |  |  |  |  |
| Mexico | LAC |  |  |  |  |
| Mozambique | AFE |  |  |  |  |
| Nepal | SAR |  | Receiving ad-hoc advisory support |  |  |
| Nigeria | AFW |  |  |  |  |
| Paraguay | LAC |  |  |  |  |
| Sierra Leone | AFW |  |  |  |  |
| Somalia | AFE |  | Receiving ad-hoc advisory support |  |  |
| Ukraine | ECA |  | Receiving ad-hoc advisory support |  |  |
| Uruguay | LAC |  |  |  |  |
| Uzbekistan | ECA |  |  |  |  |
| Zimbabwe | AFE |  |  |  |  |

Table 13. Pipeline of requested support.

# 3.  Pillar 2 — Research Program

The Research Program generates the methods, evidence and open algorithms that underpin country implementation, and feeds into the methodological guidance of the UN Committee of Experts on Big Data MPD Task Team. The streams below are drawn from the program materials reviewed for this note and should be confirmed and completed by the research leads; leads, partners and timelines are shown only where the source documents record them.

| Research stream / activity | Lead | Partner(s) | Projected | Status |
| --- | --- | --- | --- | --- |
| Access to jobs — MPD applications for labor market analysis | Milusheva | Marta Gonzalez, UCB |  | Emerging stream; featured at the 2025 Annual Meetings; 25 cities in LAC |
| Poverty measurement and targeting | Milusheva |  | Jun/26 | Paper and blog published |
| Flooding and disaster risk — filling data gaps to predict and track IDP in Africa | Milusheva, Blanchard | Moritz Meyer, Senior Economist WBG, POV | June 2026 | In progress |
| Tourism statistics methodology and open algorithm | Milusheva, Blanchard | UN MPD Task Team |  | Methodological review complete; open repository under MIT / WB IGO license planned |
| Migration statistics methodology and open algorithm | Blanchard | UN MPD Task Team |  | In progress |
| Urban mobility and transport methodology | Milusheva |  |  | Planned |
| Information society statistics methodology and open algorithm | Magpantay |  |  | Delivered |
| Pilot of privacy and privacy-enhancing technologies | Blanchard | CEGA DPL/UN PetLab |  | Ongoing |
| Reference MPD Pipeline Architecture | Blanchard | Eurostat Multi-MNO; UN MPD Task Team |  | In progress |
| Advanced research on MPD bias correction | Blanchard | University of Liverpool, Orange |  | In progress |
| Advanced research on bias arising from multi-SIM ownership | Milusheva, Blanchard | Oscar Eduardo Barriga Cabanillas, Economist WBG |  | In progress |
| Country-level research project: Rwanda | Milusheva, Blanchard | Silas Udahemuka, Senior Human Development Specialist WBG Emily Aiken, Assistant professor UC San Diego |  | Pending |
| Country level research project: Ecuador | Milusheva, Blanchard | Gustavo Javier Canavire Bacarreza, Senior Economist WBG |  | In progress |
| Country-level research project: Kazakhstan | Milusheva, Blanchard | Metin Nebiler, Senior Economist WBG |  | Pending |

Table 14. Research streams and activities — draft for confirmation by the research leads.

# 4.  Strategic Direction

At the mid-term of the Cohort 1 implementation period, the core GDF–MPD leadership team conducted a structured strategic review to assess progress, capture key learnings, and identify adaptations needed to strengthen delivery for the remainder of Cohort 1, Cohort 2 (2026–2028), and future cohorts.

Key Insights and Learnings

- Context matters. Country performance varies significantly due to institutional complexity, political economy, and implementation capacity. Larger, more process-heavy countries face slower authorization and execution dynamics than smaller or more agile counterparts.

- Uneven progress is expected and by design. The program intentionally accommodates lagging or underperforming initiatives, recognizing that MPD ecosystem development follows a non-linear innovation adoption cycle. While no formal pipeline-completion target exists, the program anticipates that approximately 30% of Cohort 1 countries will formalize MPD pipelines within the implementation period, with roughly 80% significantly better positioned for future formalization.

- Sectoral entry points accelerate value demonstration. Tourism, Transport, and Crisis Response have proven to be high-impact, lower-barrier use cases for early wins. More complex applications — such as poverty mapping and social protection targeting — require deeper institutional maturity and sustained technical support.

- Regional engagement is a force multiplier. Regional initiatives such as SADC have demonstrated strong leverage, enabling peer learning, coordinated technical assistance, and alignment with broader regional data agendas. This model is well suited to the GDF–MPD program's learning-by-doing approach.

- Vendor and technical support correlate with success. Countries progressing on schedule are frequently supported by specialized vendors — including Positium, Nommon, and UT — underscoring the importance of structured vendor engagement and technical backstopping.

- Frameworks and training programs provide a strong foundation. The Theory of Change, Country Maturity Assessment, and staged Resource Allocation Framework have proven valuable for partner coordination, resource allocation, risk mitigation, and country roadmap development. Training and workshops — particularly the Cohort 1 Launch Workshop and MPD Foundations courses — have been central to building implementation capacity.

- Ecosystem alignment remains critical. The program is well aligned with the UN MPD Task Team and complementary global initiatives such as GPSDD, positioning GDF–MPD as both a convener and an operationalizing platform for emerging standards, methods, and good practices.

- Sharpen sectoral and regional focus. Deepen investment in high-performing sectors — Tourism, Transport, Migration, and Jobs — through standardized toolkits, and expand structured engagement with regional bodies including SADC, ECOWAS, ECA, and UN Big Data Hubs.

- Strengthen governance and pipeline support. Improve support for countries stalled at the MOU and governance stage through published templates, targeted training, and focused interventions.

- Institutionalize engagement beyond individuals. TTL continuity is a major success factor. Stronger engagement at the CMU and regional levels is needed to reduce vulnerability to staff turnover and sustain institutional momentum.

- Evolve technical architecture and research integration. Explore strategic alignment with the Eurostat Multi-MNO open-source pipeline architecture and advance open algorithm development — beginning with Tourism — under WB-compatible open-source licensing.

- Adapt to a shifting operating environment. Organizational changes, procurement constraints, expiring consulting contracts, evolving trust fund rules, and a changing donor landscape all require proactive risk management and strategic repositioning.

- Position MPD and NSO nexus as a strategic asset for AI readiness. In the context of the 2026 World Development Report on AI, the program has an opportunity to help countries recognize and leverage MPD — alongside NSO data — as sovereign data assets with significant strategic value for training and validating AI solutions. As governments increasingly look to build national AI capabilities, high-quality, locally produced mobility and population data represent a foundational input that should be governed, curated, and valuated accordingly. New value propositions, like developing solutions with open weight models, should be considered.The GDF–MPD program is well placed to support countries in framing their data pipelines within a broader AI readiness agenda.

5. Program Results Indicators

| Output Indicators | Baseline | Target | Status |
| --- | --- | --- | --- |
| Number of female participants in capacity building training and workshops Unit of Measure: Number of people | 0 | 150 | Target Met (Over 250 women participation) |
| Number of Cohort Countries with formal arrangement for MPD Pipeline Unit of Measure: Yes/No | No | 8 | Target Met - (10 countries signed MOU/DSA) |
| Number of participants in trainings and workshop from LMICS | 0 | 250 | Target Met – Over 2000 participants from LMICs |
| Number of Dissemination Events | 0 | 15 | Target Met – Over 30 events |
| Intermediate Indicators | Baseline | Target | Status |
| 1st Cohort Delivered (UoM: yes/no) | No | Yes | Target Met |
| 2nd Cohort Delivered (UoM: yes/no) | No | Yes | Target Met |
| Output Indicators | Baseline | Target | Status |
| Country Cohort Work plans (UoM: yes/no) | No | Yes | Target Met |
| Public Goods (frameworks, templates, training materials, etc): (UoM: yes/no) | No | Yes | Target Met – Over 20 knowledge assets delivered |