| Country Team / TTL | Project title / use case | MOU status | Maturity | Top-up (Y/N) | Notes |
| --- | --- | --- | --- | --- | --- |
| Argentina | Dynamic population mapping; information society statistics | No MOU documented | Pre-Foundation | N | - Telefonica sale put a pause on Regulator engagement with the project. - ITU Magpantay has established contact with a separate government team - Marianna is considering options |
| Benin | Dynamic population mapping; tourism statistics | No MOU documented | Pre-Foundation | N |  |
| Brazil | Transport and mobility statistics | MOU signed | Practitioner | N | -Stakeholder workshop in Brasilia (Feb 2025): 100+ representatives from ANATEL, Ministry of Cities, IBGE, SERPRO - Origin-destination matrices and mobility pilots launched for Florianópolis, Rio de Janeiro, and Belém - MPD analytics integrated into Brazil Electromobility MPA (electric bus transition) - DRM use case added following 2024 Rio Grande do Sul floods --LAC regional hub engagement (IBGE / ENCE) - Origin-destination matrices and mobility pilots completed for Florianópolis, Rio de Janeiro, and Belém - Analytical use case for Salvador urban transport, including providing concrete policy insights (completed in July 2026) - Final capacity building workshop planned for November 5, 2026, where the first half of the day will focus on the presentation of the policy insights emerging from the analytical case studies (Salvador urban transport, Rio Grande do Sul DRM, plus a presentation by IBGE on their efforts to develop a proof of concept with CDR for commuting statistics), and the second half of the day will be hands-on training on CDR use and caveats. I’m attaching the save-the-date if useful. |
| Côte d’Ivoire | Dynamic population mapping; migration statistics | MOU drafted, not signed | Pre-Foundation | N | - Hosted the ECOWAS MPD for Statistics Workshop, Abidjan, Mar 2026; founding member of the ECOWAS Technical Working Group. - MOU drafted with Orange. |
| Ecuador | Transport statistics; poverty mapping | MOU signed | Foundation | Y | - MOU signed - Pipeline provisioned; active data use under way. Strong Foundations Course uptake across INEC, MTOP, the Quito Secretariat of Mobility and OTECEL. - Use cases: national road network model, Quito Metro impact, canton-level poverty mapping. OTECEL dataset acquired with two weeks of QA technical support First interinstitutional MPD technical team created (INEC, MIT, OTECEL) - ML poverty estimation model developed (consultant from Universidad Carlos III de Madrid) - Informing Emergency Resilient Reconstruction Project (P181079) and Quito Metro Line One Phase II (P511841) |
| Guinea | Transport; urban mobility | No MOU documented | Pre-Foundation | N |  |
| Haiti | Dynamic poverty mapping for social assistancetargeting | MOU drafted; existing DSA with Digicel (via Flowminder) under renewal | Foundation | N | - Counterparts include IHSI, MAST, DGPC and CNSA. - Flowminder-Digicel data sharing arrangement has been renewed – Flowminder are producing statistics with Digicel data - Digicel have also formally recognized Flowminder’scollaboration with the World Bank and IHSI. - Supporting IHSI to pursue a (direct) data sharing agreement with Natcom, Haiti’s second largest MNO (Sep 26) - Using Digicel’s MPD (processed by Flowminder) to help build/validate an integrated master sample for Haiti’s upcoming household surveys |
| India | Public health; crisis monitoring, Tourism | MOU signed | Foundation | Y | - It is among the first major studies in India to leveragehigh-volume mobility data to systematically map tourist movement patterns. - The scale and volume of data used are unprecedented for a tourism analytics exercise in the country. - Letter of Intent signed between Government of Maharashtra and Reliance Jio (Jul 2025) - Pilot completed mapping tourist patterns across Maharashtra with Jio, MITRA, Department of Toursim. - Preliminary results presented to Ministry of Tourism and MoSPI; featured at National Workshop on Alternate Data Sources (Jun 2025) - Preliminary tourism results circulated and reviewed through Bank processes (Jul 2026) - Top-up (Phase 2): scaling in Maharashtra through Bank lending operation and a second state (Goa or Odisha) |
| Kazakhstan | Tourism statistics (domestic and inbound) | MOU signed (Nov 2024); parliamentary decree mandating MPD sharing from Jan 2026 | Practitioner | Y | - MOU signed (Nov 24) - Advanced implementation with top-up funding. - Legislative mandate extends data sharing to all MNOs from Jan 2026. - Tourism statistic phase one official statistics launched at Digital Bridge, Astana, 30K attendees (Oct 2025) - Preliminary tourism statistics showed 2.4x–4x underreporting vs. official records (Jun 2025) - Advanced to Practitioner stage; multi-MNO integration and inbound tourism statistics underway - BNS ICC team took over all script development in-house, ensuring pipeline sustainability - Ministry of Tourism and Sport formally integrating MPD findings into infrastructure and strategic planning - First country in the CIS to transition MPD-derived indicators into official statistics - ICC produced a first set of commuting and migration statistics (June 2026) |
| Kenya | Dynamic population mapping; disaster response; transport | MOU signed Jul 26 | Foundation | Y | - MOU signed with Safaricom; KNBS, CA and ODPC engaged. Global Data Festival and Kenya Space Expo, Nairobi (Jun 2026) |
| Mongolia | Migration and information society statistics | MOU signed (2025) | Foundation | Y (proposal submitted) | -GDF workshop (Oct 2024): stakeholders aligned on migration use case for nomadic/rural-to-urban mobility gaps - -Tripartite MoU signed: Mobicom, CRC, and NSO (Jul 2025) - Follow-up workshop (Apr 2025) with Positium and ITU on data privacy and best practices - Phase 3 proposal submitted (Sep 26) - First use case completed: population and internal migration statistics; pipeline validated at National Data Center - Reached "Practitioner" maturity stage - Top-up: domestic tourism indicator framework under development; Phase 3 proposal submitted (Sep 2026) |
| Morocco | Dynamic vulnerability mapping; social assistance; migration | Pre-MOU | Practitioner | N | - Near-practitioner maturity despite pre-MOU status. - National workshop delivered in May 2026, convening NSO, Regulator and MNOs - Ongoing review of regulatory framework and preparatory negotiations for MOU |
| Peru | Disaster response; public health | DSA signed with INEI | Foundation | N | - Hosted GDF-MPD program at IPC Business Summit session, Lima, (Sep 2025) - DSA signed between INEI and the World Bank (May 26) |
| Rwanda | Vulnerability mapping; social assistance | MOU Pending | Foundation | N | - High-Level Roundtable (April 2025)Government(Ministry of Local Government, NISR, RISA, RURA), MNOs (MTN, Airtel), and development partners secured buy-in for MPD integration into ImiberehoSocial Registry. - MINALOC formally requested sample MPD dataset (5,000–20,000 subscribers) from RURA for operational research. - Multi-agency Technical Working Group formed (MINALOC, RISA, NISR, RURA). - Further exploration of MPD included in the Additional Financing for Social Protection Transformation Project (P177492). - Roundtable hosted by MINALOC, NISR, and RURA (July 2026) – Signed minutes attached - Revised DSA agreed by all parties; signature pending (August 2026) – Follow on meeting to unlock any pending issue planned during the week of September 12. |
| Senegal | Urban mobility and transport | MOU drafted | Foundation | N | - Research on temporary migration patterns under way. Member of the ECOWAS Technical Working Group (launched Abidjan, Mar 2026). - MOU drafted with Orange; ARTP engaged. |
| The Gambia | Dynamic population mapping; migration; urban mobility | MOU signed; Data License Agreement signed (2-year auto-renewable) | Foundation | N | - Tranche 1: study tour to Ghana; ECOWAS workshop; use case and IT pipeline developed; MPD Academy in The Gambia (June 2025); - MOU signed between PURA and GBoS; online GDF-MPD training completed. - Scale-up under the Stats Project, extension of the use case, and local literacy and capacity building. - GBoS is core member of the ECOWAS Technical Working Group (launched Abidjan, Mar 2026). - PET technology provisioned and training provided (May 2026). - WB DSA signed between PURA and WBG; PURA acts as data custodian and licensor (August 2026). |
| Togo | Migration and tourism statistics | No MOU documented | Pre-Foundation | N |  |
| Tunisia | Vulnerability mapping; social assistance; internal migration indicators | MOU drafted; letter to MNOs issued (Jun 2024) | Practitioner | N | - Letter to MNOs issued Jun 2024 - Country workshop convened (24) - technical meetings and a national workshop convened (Mar 25) |